Weekly Progress — Receptor Resurfacing Pipeline

15–22 April 2026 · Pikp1-HMA / AvrPikD system

## Summary

The negative-steering workflow has now been integrated as a module in the NextFlow receptor resurfacing pipeline (HADDOCK → RFDiffusion → Rosetta → ProteinMPNN → Boltz-2 negative steering → orthogonal metrics). Test run of 16 MPNN sequences through the negative steering module yielded 7 candidates with unanimously correct effector placement agreement, and 2 candidates with 2/3 samples agreeing. Post-steering orthogonal-validation metric module (interface-restricted metrics, AF3-no-MSA, Rosetta, biophysical) is built and test-validated, and needs to be integrated into the main pipeline.

## Priority tasks completed

- Contamination fix (Tasks 1, 12): contact-based gate in production — any steering mutation contacting the effector in the final prediction contaminates, regardless of position.

- Composite ranker (Tasks 2, 3, 4): true_jaccard − 0.05·ra_eff shipped; confidence metrics populated for all rows; rank_by_ipsae_min retired. Next steps: including weighting by distance and close-tie breakers.

- NextFlow integration (Task 5): Standalone SLURM chain replaced by a single NEGSTEER_RUN_ONE process, replacing legacy boltz2.nf.

- Container rebuild + kernel decision (P0-30, P0-35): boltz2_negsteer.img rebuilt from scratch with pinned deps (torch 2.6.0+cu124, cuequivariance 0.9.1) and four drift-prevention checks. Runtime A/B test showed kernels are ~5% slower at our protein size → production keeps kernels off. Both build- and runtime-acceptance met.

## New additions

- Interface-restricted metrics (P0-29): new module + 7 new columns (iRMSD, fnat, DockQ, ipSAE@15 Å as well as at 10 Å, intact_core). Runtime ~1 min.

- Orthogonal validation cascade (P0-31): AF3-no-MSA (GPU) + FreeSASA/MDAnalysis/pLDDT (CPU) + Rosetta Sc+ΔΔG single InterfaceAnalyzer call (CPU), merged via filter cascade. Runtime ~15–20 min (mostly AF3).

- Multi-seed prediction (--num-seeds N), reversion deduplication, per-sequence aggregation (median + MAD), rewritten extract_passing.py, one-shot submit_postprocess.sh.

## Validation runs

| Run | Outcome |
| --- | --- |
| 200-prediction variance test (20 sequences, 10 samples) | ipSAE does not distinguish correct vs. incorrect interfaces on this system → rank_by_ipsae_min retired; ipSAE demoted to a plus-factor. |
| 16-sequence overnight (first production NextFlow) | 7 tier-A, 2 tier-B, 7 tier-none; design_3 strongest (3/4 tier-A). Validated patches v3 at production scale. |
| Kernel A/B (matched, d=5) | cuEquivariance kernels ~5% slower on our ~155-residue complexes (+4.5 s/prediction). Decision: keep negsteer_no_kernels=true in production. Container rebuild still valuable for dependency hygiene. Reducing seed count 5->2 yields only 20% improvement in speed: diffusion step not limiting factor. |

## Parallel cleanup of the outer pipeline

Full per-block audit complete:

- HADDOCK (12 fixes, test-validated)

- RFDiffusion (9 fixes including three high-severity bugs surfaced by multi-denovo testing)

- Rosetta filtering (5)

- preprocessing (3)

- ProteinMPNN overhaul (receptor_start_pdb plumbing, RESOLVE_CONTIGS process, R7/R12 cross-pollination and RMSD fixes, H15 consolidation). Next steps: Parallelise

- Legacy AF2-monomer/FASTA branch removed; container paths consolidated across main and five per-module test scripts.

## Biggest bugs caught

- Multi-seed reversion harvest was discarding 2/3 of GPU work (cycle-N+1 rows keyed on a non-unique index).

- Gated new_contamination bug — post-reversion contamination check was hiding the majority of the pipeline's actual successes; only surfaced by comparing v11 expected-vs-actual tier counts.

- Four-iteration effector-atom filter fix — v8 atom-level on Cα-only ground truth failed, v9 residue-level with wrong resseq failed, v10 landed with positional indices.

## Strategy / methodology decisions made this week

- Design-region strategies:

    - Strategy 1: Only change residues whose side chains point outwards.

    - Strategy 2: Known important + variable residues.

    - Strategy 3: Whole interface redesign.

    - Strategy 4: 8 Å shell from effector hotspots.

- Scoring philosophy: DockQ-vs-experimental-structure as the dominant ranker term (genuine ground truth, not self-consistency), supported by geometric consistency (placement + weighted Jaccard with smooth distance weighting), with energy metrics secondary. ipSAE/ipTM explicitly demoted.

- Autoactivity risk framing: full-length receptor NBD-LRR interface RMSD vs. native autoinhibited state as a computational pre-filter for high-priority designs.

## Key scientific findings

- ipSAE/ipTM are unreliable on this system — fluctuate between samples of identical sequences and respond dramatically to off-interface residue movement. Geometric metrics (true_jaccard, ra_eff, iRMSD/DockQ) are the trustworthy signal.

- Contamination is contact-based, not position-based — no position-based exemptions are defensible.

- Speedup priority has flipped: diffusion samples account for only ~27% of per-prediction wall time; the remaining ~73% (~62 s of 86 s) is fixed overhead per boltz predict invocation (model load, featurization, trunk forward pass, I/O). Biggest theoretical win is batching multiple inputs through one invocation or holding the model in a persistent process — not the kernel or diffusion loop.

## What's next (per todo_list v5)

- P0-34 (mechanical): wire interface + orthogonal metrics modules into main.nf. Test harness is green; copy-and-simplify.

- P0-38 (new, promoted from P1): weighted Jaccard with smooth distance weighting. Elevated to P0 because landing it after the three-target Task 7 run would force reprocessing.

- Task 6: scrambled / all-glycine negative controls — scoped at ~100–150 lines (NEGSTEER_CONTROLS process, row_type column, --run-negative-controls flag); lands alongside P0-34.

- Task 7: three MAX effectors × Pikp1-HMA — first true cross-task generalisation test, unblocked by this week's infrastructure.

- Forward track (from notes 11): generative ESM-2 for steering-mutation proposals (trained on NextFlow production data as a free byproduct); separate orthogonal ESM-2 scoring model to be trained once plant-cell-pack assay data arrives.